**The Town of Clarkson Water Improvement Benefit Area No. 1**

**February 1, 2025**

The Town’s engineers, MRB Group, provided the following update:

* As of January 17th, the Contractor has installed approximately 31,000 linear feet of water main along portions of Drake Road, Redman Road, and Monroe Orleans County Line Road.
* The schedule below outlines the remainder of the watermain installation for the project.
* Restoration of the areas disturbed during construction will occur after the attached schedule as the weather allows and should be completed by the end of May 2025.
* Eligible residents within the water district who have not signed up and would like to, are encouraged to call Monroe County Water Authority as soon as possible. Contact Virginia Smith, New Services, 442-2001, Ext. 229 or email: Virginia.Smith@mcwa.com.
* Feel free to contact Scott Mattison, Project Engineer, 585.340.3661 with any questions.

**Pilon Construction Co., Inc., 13205 Route 31 Albion, NY 14411**

|  |  |
| --- | --- |
| County Line Road | 01/06/2025-01/22/2025 |
| Redman Road | 01/23/2025-02/03/2025 |
| West Ave./Old State Rte. 31 | 02/04/2025-02/20/2025 |
| Lawton Road | 02/21/2025-03/05/2025 |
| Ireland Road | 03/06/2025-03/18/2025 |
| Sweden Walker Road | 03/19/2025-03/28/2025 |
| Horizontal Drilling | 02/03/2025-03/28/2025 |